## Sheet1
SERIAL | ISSUES | STATUS
1 | When we give entry in collection schedule the pop up shows that “Branch Code Required”. | Resolved
2 | DD report and entry data MISMATCH | Resolved
3 | After delete one Instrument we giving fresh entry but the fresh entry not counted as new entry and not printed as a letter | Resolved
4 | After marking an Instrument from Paid to outstanding and again Paid the instrument not reflect in funding file (Wednesday issue) | Not Tested
5 | In DD detail Most of Drawee bank branch are absent such as Ramna Branch, Principal branch | Resolved
6 | In Citispeed and Citicash summery, Citicash repost and Citi speed report the instrument number not shown | Partially resolved
7 | Our clearing team found MISMATCH in entry on DD detail though it is ok at our end (ref: 05545) | Resolved
8 | Total Instrument number and Grand total In amount needed In all report(Enhancement) | Partially resolved
9 | Can not take Reprint and remove date range | Partially resolved
10 | For same Check number status not shown | Unresolved
11 | Bank wise serial needed for reminder | Unresolved
12 | Need rec formate file | Unresolved
13 | After marking the return in anywhere the return Instrument not shown in report | NEW ISSUE
14 | Can generate funding file multiple time Enhanchment needed | NEW ISSUE
15 | Total Amount of client deposits are not showing in Reports | NEW ISSUE
16 | Monthly Bill for Cash Management Services Report is not showing | NEW ISSUE
17 | Need inclusion of Deposit Date Column in Schedule Authorization Screen | NEW ISSUE